## E36
No. | Description | Unit | Unit price(USD) | NetOne Chitsanga Chiredzi
|  |  |  | Quantity | Total
1 | Engineering Costs
| Fundamental Planning | hr | 27 | 1 | 27
| Outside Plant Evaluation ( Site and Route Surveys) | hr | 50 | 1 | 50
| Planning, Design and Design Reporting | hr | 27 | 1 | 27
| Material Mobiliation | ea | 500 | 1 | 500
| As -built Documentation | hr | 23 | 1 | 23
| Engineering Costs |  |  |  | 627
2 | Construction
| Trenching Normal Soil | m | 3.7 |  | 0
| Backfilling | m | 1.5 |  | 0
| HDPE pipe laying | m | 0.3 |  | 0
| Duct Clearing | m | 0.3 |  | 0
| Cable blowing (microduct) | m | 0.3 |  | 0
| Cable laying Duct | m | 0.3 |  | 0
| Overhead Cable Pulling | m | 0.3 | 5500 | 1650
| LAN cable pulling | m | 0.22772 |  | 0
| Overhead Cable Binding | m | 0.15 | 5500 | 825
| Pole fixing | ea | 1 |  | 0
| Hole digging | ea | 4.8 | 55 | 264
| Pole Planting | ea | 2.5 | 55 | 137.5
| Pole Preparation | ea | 1 | 55 | 55
| Stay Wire Preparation | ea | 5 | 11 | 55
| Cabinet mounting | ea | 25 | 1 | 25
| Bush cutting (Variable) | sq m | 0.2 |  | 0
| Handhole installation Preparation | ea | 40 |  | 0
| Handhole installation | ea | 20 |  | 0
| Trust Boring Preparation | ea | 30 |  | 0
| Configurations | hrs | 50 | 1 | 50
| Cable Termination | ea | 10 | 2 | 20
| Cable Splicing | splice | 10 | 3 | 30
| End to End Testing | ea | 250 | 1 | 250
| Labour |  |  |  | 3361.5
3 | Reinstatement (fix & supply) | m | 35 |  | 0
4 | Wayleaves
| Clearance Fees (ZESA, etc) | map | 40 |  | 0
| Council Trenching Fees | m | 0.58 |  | 0
| road crossings |  | 500 |  | 0
| EMA |  |  |  | 0
| Wayleaves |  |  |  | 0
5 | Other
| Damage to Others Infrastructure |  |  |  | 0
6 | Transport |  |  |  | 0
| Lorry | km | 2 | 16 | 32
| Truck | km | 1.5 | 80 | 120
| Passenger | km | 1.6 |  | 0
| Total Transport |  |  |  | 152
7 | T&S
| T&S TT | days | 54 |  | 0
| T&S Engineer | days | 54 |  | 0
| T&S TA | days | 54 |  | 0
| Total T&S |  |  |  | 0
8 | Materials
| 2 core drop cable | m | 0.4 |  | 0
| 4 core drop cable | m | 0.42 |  | 0
| 6 core ducted cable | m | 0.6 |  | 0
| 12 core ducted cable | m | 0.9 |  | 0
| 24 core ducted cable | m | 1.5 |  | 0
| 48 core ducted cable | m | 2 |  | 0
| 96 core ducted cable | m | 3 |  | 0
| 6 core microducted cable | m | 0 |  | 0
| 12 core microducted cable | m | 0.5 |  | 0
| 24 core microducted cable | m | 0.7 |  | 0
| 48 core microducted cable | m | 0.9 |  | 0
| 96 core microducted cable | m | 2 |  | 0
| 6 core ADSS | m | 0.8 |  | 0
| 12 core ADSS | m | 1.2 |  | 0
| 24 core ADSS | m | 1.8 | 5500 | 9900
| 48 core ADSS | m | 2 |  | 0
| 72 core ADSS | m | 3 |  | 0
| Wooden Pole (7.5m) | m | 30 | 44 | 1320
| Wooden Pole (10m) | ea | 40 | 11 | 440
| Dead end binder | pcs | 9.56 |  | 0
| Middle span binder | pcs | 7.33 |  | 0
| Dead end set | pcs | 22 | 11
| Mid span set | pcs | 22 | 44 | 968
| single hook | pcs | 1.58 |  | 0
| double hooks | pcs | 2.1 |  | 0
| Downlead clamps |  | 22 |  | 0
| 24-port Cisco switch | ea | 1050 |  | 0
| 48-port PoE switch | ea | 1500 |  | 0
| stay set | set | 50 | 11 | 550
| slack storage | pcs | 22 | 2 | 44
| O/H Junction Closure | ea | 100 |  | 0
| U/G Junction Closure | ea | 200 |  | 0
| GI Pipe | m | 10 |  | 0
| HDPE pipe | m | 2.8 |  | 0
| Warning Tape | m | 0.5 |  | 0
| Media Converter 15Km | ea | 90 | 2 | 180
| Mikrotik Router(wifi) / TP Link AP | ea | 120 |  | 0
| Cisco 1941 series router | ea | 1500 |  | 0
| 8 Port Switch (POE) | ea | 72 |  | 0
| Ubiquiti indoor Aps | ea | 160 |  | 0
| Ruckus Indoor wireless AP | ea | 600 |  | 0
| Ruckus outdoor wireless AP | ea | 900 |  | 0
| 1G 20km Cisco SFP | ea | 200 |  | 0
| Baudcom Mux 4FE + 8 POTS | ea | 350 |  | 0
| Baudcom Mux 4FE + 30 POTS | ea | 425 |  | 0
| Baudcom Mux 4FE + 256 POTS | ea | 8000 |  | 0
| 4 Port IAD (FXO) | ea | 290 |  | 0
| 8 Port IAD (FXO) | ea | 290 |  | 0
| 4U Cabinet | ea | 120 |  | 0
| 6U Cabinet | ea | 250 | 1 | 250
| 9U Cabinet | ea | 450 |  | 0
| 15U Cabinet | ea | 550 |  | 0
| 25U Cabinet | ea | 750 |  | 0
| Fibre Patch Panel | ea | 45 | 1 | 45
| Ethernet Patch Panel 24 port | ea | 45 |  | 0
| Brush Tide | ea | 87 | 1 | 87
| Surge protector 4 Way Power Adapter | ea | 30 | 1 | 30
| Join Trunking 16x40-L | ea | 2.5 |  | 0
| Join Trunking 16x40-T | ea | 2.5 |  | 0
| Trunking 40x46mm | ea | 3 |  | 0
| Trunking 16x40mm | ea | 2.5 |  | 0
| Trunking 16x25mm | ea | 3 |  | 0
| Trunking 25x40mm (3m length) | ea | 4.25 |  | 0
| Trunking 100x40mm(3m length) | ea | 25 | 1 | 25
| Trunking 40x40mm | ea | 5.75 |  | 0
| cat 5e indoor | ea | 1.3 |  | 0
| 1/2 moon conduit pipe (5m) | ea | 10 |  | 0
| CAT 6 indooor | ea | 1.5 |  | 0
| CAT 6 outdooor | ea | 2 |  | 0
| Ethernet single Face Plates | ea | 5 |  | 0
| Ethernet back boxes | ea | 5 |  | 0
| 0.5m fly lead | ea | 1 |  | 0
| 1m fly lead | ea | 3.8
| 3m Fly lead | ea | 6.8 |  | 0
| Mid-couplers ST-ST | ea | 40 | 2 | 80
| Pig tails (3m) | ea | 10 | 1 | 10
| Patch Cord (3m) | ea | 5 | 1 | 5
| Splicing Sleeves | kg | 12 |  | 0
| Insulation Tape | ea | 5 |  | 0
| RJ 45 connectors | ea | 0.3 |  | 0
| Staples | ea | 0.5 |  | 0
| Fisherplugs(Box) | ea | 2 |  | 0
| Cable Ties | ea | 0.3 | 20 | 6
| Wood Screws | ea | 0.2 |  | 0
| Rawl Bolts | ea | 2 | 4 | 8
| Cage nuts | ea | 3.6 | 1 | 3.6
| handhole | ea | 530 |  | 0
| Subtotal |  |  |  | 13951.6
| 5% Contingencies |  |  |  | 697.58
| Total Materials |  |  |  | 14649.18
| Grand Total (Materials, Transport, Labour, Wayleaves and Engineering costs) |  |  |  | 18789.68

## Sheet1
12 core ADSS | 1.2 | 700 | 840
Wooden Pole (7.5m) | 30 | 12 | 360
Dead end binder | 9.56 | 12 | 114.72
Middle span binder | 7.33 | 5 | 36.65
Dead end set | 22 | 12 | 264
Mid span set | 22 | 5 | 110
Media Converter 30Km | 120 | 2 | 240
Mikrotik Router(wifi) / TP Link AP | 120 | 1 | 120
Ruckus Indoor wireless AP | 600 | 2 | 1200
25U Cabinet | 750 | 1 | 750
Fibre Patch Panel | 45 | 1 | 45
Ethernet Patch Panel 24 port | 45 | 1 | 45
Surge protector 4 Way Power Adapter | 30 | 2 | 60
CAT 6 indooor | 1.5 | 300 | 450