## Fuel Expenditure
Fuel Consumption Analysis
Month | Week | Petrol Consumed | Diesel Consumed | Total for Week | Total for Month
July | 27 | 360 | 200 | 560
| 28 | 476 | 232 | 708
| 29 | 330 | 220 | 550
| 30 | 343 | 189.2 | 532.2
August | 31 | 350 | 189.2 | 539.2
| 32 | 540 | 116 | 656
| 33 | 540 | 116 | 656
| 34 | 472 | 60 | 532
September
|  | Total Fuel Consumed |  | 4733.4

## Jobs Analysis
Jobs Analysis
Item | Month | Week of the Year | Number of Jobs | Average Turn Around Time (Days)
1 | July | 27 | 3 | 3
2 |  | 28 | 3 | 5.67
3 |  | 29 | 4 | 6
4 |  | 30 | 2 | 7.5
5 | August | 31 | 2 | 14
6 |  | 32 | 4 | 6.5
7 |  | 33 | 6 | 7
8 |  | 34 | 10 | 3.64
September
Average

## Simple Quotation Analysis
Simple Quotation Analysis
Item | Month | Week of the Year | Number of Simple Quotations Completed (hrs) | Simple Quote Average Turn Around Time (Hrs) |  | Average
1 | July | 27 | 18 | 3.2
2 |  | 28 | 15 | 3.3
3 |  | 29 | 11 | 3.5
4 |  | 30 | 13 | 3.4 | Monthly Average | 2.8
5 | August | 31 | 17 | 2.7
6 |  | 32 | 10 | 3.75
7 |  | 33 | 12 | 4.5
8 |  | 34 | 8 | 2.25 | Monthly Average | 3.3
9 | Sedptember
10
11
12
13 |  |  |  |  | Monthly Average

## Complex Solution Analysis
Complex Solutions Analysis
Item | Month | Week of the Year | Number of Solutions | Solutions Average Turn Around Time (Days) | Monthly Average
1 | July | 27 | 0 | 0
2 |  | 28 | 1 | 3
3 |  | 29 | 0 | 0
4 |  | 30 | 0 | 0 | 1.1
5 | August | 31 | 0 | 0
6 |  | 32 | 0 | 0
7 |  | 33 | 0 | 0
8 |  | 34 | 0 | 0 | 2.6
9 | September
10
11
12
13 |  |  |  |  | 3.25

## New Jobs Received
New Jobs received Analysis
Item | Month | Week Under Review | Number of New Jobs received | Name of Job/s Received
1 | July | 27 | 4
2 |  | 28 | 4
3 |  | 29 | 7
4 |  | 30 | 5
5 | August | 31 | 6
6 |  | 32 | 10
7 |  | 33 | 10
|  | 34 | 15
8 |  | 35 | 15
9 | September
10
11
12
13

## Training Received
New Jobs Analysis
Item | Week of The Year | Trainings Received | Persons Trained
1 | 27 | 0 | 0
2 | 28 | 1 | 1
3 | 29 | 0 | 0
4 | 30 | 2 | 3
| 31 | 2 | 3
5 | 32 | 0 | 0
6 | 33 | 0 | 0
7 | 34 | 1 | 3 | Data Analytics training in progress
8
9
10
11

## Jobs Handed Over
Jobs Handed Over to Operations 2023
Item | Month | Week of the Year | Job Handed Over | Client Name of Job Handed Over
1 | July | 27 | 0
2 |  | 28 | 1 | ZIMDEF Masasa
3 |  | 29 | 4 | DFA American Embassy
Battery Whole GraniteSide
Intercane Unit L
4 |  | 30 | 0
7 | August | 31 | 4 | Stanbic Acckland
CUTRAG Frampol
ZRP Warren Park
ZEC Bindura
9 |  | 32 | 3 | Ok Zim G/Noarh
ok Zim Queesdale
Victoria Foods WoolWhich
10 |  | 33 | 3 | OK Zimbabwe Glen Norah
11 |  |  |  | OK Zimbabwe Queensdale
12 |  |  |  | Victoria Foods Woolwich
13 |  | 34 | 0
14
15
16
17
18 | September
19
20
21
22
23
24
25

## Mini-Project Analysis
Mini-project Analysis 2023
Item | Month | Week of the Year | Mini-project | Planned Project Costs | Actual Project Cost | Cost Variance % | Planned Project Imp Time | Actual Project Imp. Time | Impl Time Variance | Comments
1 | July | 27 | 0
2 |  | 28 | 0
3 |  | 29 | 0
4 |  | 30 | ZRP CID
ZEC BINDURA
AirForce Manyame
8 | August | 31 | Glen Norah
Karo Platinum
Cowdray Park smart city Wi-Fi
11 |  | 32 | 0
12 |  | 33
13 |  | 34 | Presidents Department Greendale
14
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38

## Questionnaire Analysis
Questionnaire Analysis 2023
Item | Week of the Year | Number of Questionnaires Submitted | Average Score for all Questionnaire Items
July | 27
29
August
| 34 | 0 | 0

## All Completed Jobs
All Completed Jobs Analysis 2023
Item+A2:I2 | Month | Week of the Year | Job or Mini-project | Service Type | Fibre Type | Fibre length | Job completion form | Customer Questionnaire | Job Hand-over | Installation revenue (Installation Costs) | Re-current revenue
1 | July | 27 | Sithole GALA and Manifesto Launch | 2 Radio stations and ZBCTV
|  |  | ZANU PF Chipinge | Internet
2 |  |  | DFA American Embacy | 100Mbps
3 |  | 28 | ZRP Warren Park | Internet
|  |  | Frampol Cat Rag | VPN
|  |  | New AirPort Relocation | Relocation from old terminal server Room to new terminal Telecoms Room
|  |  | Bindura University Guest Logde | 15 Mbps Internet
|  |  | Bindura University Guest Logde | 15 Mbps Internet
|  |  | Bindura University Guest Logde | 15 Mbps Internet
|  |  | Airport Core Of Zim | 100 Mbps Upgrade
|  |  | POTRAZ CIC Mapunzure VSAT ,VOIP ,ISDN | Internet
|  |  | Airport Company Zimbabwe | 2X E1S
4 |  | 29 | Profeeds Rutenga | 2Mbps Internet
5 |  |  | Met Office Kariba | Internet
6 |  |  | CAZ Airport Official Opening | 100Mbps Internet Upgrade
7 |  |  | CAZ Airport Official Opening Rally OB | 100Mbps Internet
8 |  | 30 | ZEC Bindura | VPN 10Mbps + LAN
9 |  |  | AirForce Manyame | VPN
10 |  |  | ZRP Old CID Office | 2Mbps
11 |  |  | FBC Harve Brown | 3Mbps Internet
|  |  | Morgan ZINTEC College | Fibre LAN
|  |  | ZANU PF Centenary Rally | Internet
|  |  | Zanu PF Glendale Gala | Internet
| August | 31 | OK Zimbabwe Glen Norah | VPN
|  |  | Karo Platinum | 5Mbps
12 |  |  | Cowdray Park Smart WiFi - Terminus | 100Mbps
|  |  | Victoria Foods | VPN
|  |  | DFAZ Afrix | Cross connection
|  |  | DFAZ Terraco Isando | Cross connection
|  |  | DFAZ Stan Chart | Cross connection
|  | 32 | Nedbank 3rd Street | VPN and VoIP
|  |  | Nyaradzo JOINA | VPN
|  |  | Powerspeed Graniteside | VPN (Camera)
13 |  |  | ZBC OB CCTs Mutawatawa | VPN and Internet
32
14 |  | 34 | FAZ Borrowdale | LAN | None
15 |  |  | OPC Greendale | 20 Mbps VPN
16 |  |  | ZRP Morris | LAN Ext
17 |  |  | FAZ Chaminuka | VPN
18 |  |  | ZTN HICC | 20Mbps Internet
19 |  |  | ZBC TV HICC | OB CCT 20Mbps
20 |  |  | ZEC HICC | IP/PBX AND LAN
21 |  |  | ZEC Seke | TrnasferVPN and LAN
22 |  |  | ZBC National FM | 5Mbps Internet
23 |  |  | ZBC Radio Zimbabwe | 5 Mbps Internet
24 |  |  | ZRP HICC | 5 Mbps
25 |  |  | OMNI Africa | SIP Line Configurations
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50 |  | 11
51
52
53
54
55
56
57
58
59 |  | 12
60
61
62
63
64
65
66
67
68
69
70
71 |  | 13
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94

## Budget vs Actual Analysis
All Completed Jobs Cost Analysis 2023
Item | Month | Week of the Year | Job or Mini-project | Budget Base Line | Actual Cost | Actual as Percentage of Budget Target 90% | Job completion form submmitted
1 | April | 14 | Metbank Premier Floors
2 |  |  | Women University in Africa
3 |  | 15 | Ministry of Environment and Tourism
4 |  |  | Ministry of Youth Quality International Hotel
5 |  |  | Ministry of Home Affairs
6 |  |  | Frampol Pro Dairy Ruwa
7 |  |  | Presidents Department Mwenezi branch
8 |  |  | Zimbabwe Lands Commission Gweru
9 |  |  | Women University in Africa
10 |  | 16 | Chivaraidze Farm Clinic
11 |  |  | FBC Mvurwi
12 |  |  | ZACC Herbert Chitepo Complex
13 |  |  | New Parliament Mt. Hampden
14 |  |  | ZIMRA Beitbridge
15 |  |  | Presidents Department x 6 Sites
16 |  |  | ZEC Makombe
17 |  |  | ZEC Makombe
18 |  |  | Meikles Hotel
19 |  |  | Africom Causeway
20 |  |  | ZBC x 5 stations Mt Darwin
21 |  |  | GISP Mt. Darwin
22 |  |  | ZIMPAPERS x 2 Mt. Darwin
23 |  |  | ZARNET Mt Darwin
24 |  |  | Sprayview Hotel
25 |  |  | Cell Insurance Ngezi Turf Club
26 |  |  | Cell Insurance Chegutu
27 |  |  | FBC Mvurwi
28 |  |  | NetOne Mt. Darwin
29 |  | 17 | FAZ Borrowdale
30 |  | 18 | Farm and City Kwekwe
31 |  |  | Grant Thornton
32 |  |  | Innovative Technologies
33 |  | 19 | Meng Bertha
34 |  |  | GISP Chivhu
35 |  |  | Zimbabwe Lands Commission
36 |  |  | Civil Registry E-Passport
37 |  |  | Care Zimbabwe Murambinda
38 |  |  | Appliance Expert Kwekwe
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75 | April
76
77